## Road Map
Service General - Road Map
|  |  | Release 1 |  | Release 2
Application Modules | Feature Backlog | Story Points | Iteration 1 - 10/14/21 | Iteration 2 - 11/04/21 | Iteration 3 - 11/18/21 | Iteration 4 - 12/17/21
1. User Account | 1.1 Create an Account (Spring 2021)
1.2 Sign into Account (Spring 2021)
| 1.3 Delete an Account | 3 | x |  |  |  | i1 | i2 | i3 | i4
| 1.4 Update Profile | 4 |  | x
| 1.5 Account Logout | 5 |  | x
1.6 Account Verification
2. Customize Search | 2.1 Search by Location | 5 |  |  | x
| 2.2 Search by Keyword | 5 |  |  |  | x
| 2.3 Search by Service | 5 |  |  | x
2.4 Best Rating Search
3. Job Advertisement | 3.1 Create Advertisement Service Request | 4 |  |  | x
| 3.2 Close Advertisement Service Request | 4 |  |  | x
4. Job Service Request | 4.1 Register Job Service (Spring 2021)
| 4.2 Submit Job Service Request | 4 | x
| 4.3 Accept Job Service Request | 3 | x
| 4.4 Display Service Request Dashboard | 3 | x
| 4.5 Decline Job Service Request | 5 | x
5. Payment | 5.1 Add Payment Information | 4 |  |  |  | x
| 5.2 Update Payment Information | 4 |  |  |  | x
| 5.3 Delete Payment Information | 3 |  |  |  | x
6. Control Management | 6.1 Manage Accounts
6.2 Manage Map
6.3 Manage Advertisements
6.4 Manage Payment
7. Feedback System | 7.1 Create Feedback (Spring 2021)
| 7.2 Edit feedback | 5 |  | x
| 7.3 Delete feedback | 5 |  | x
| 7.4 Rate Service | 5 |  | x
|  | Velocity | 18 | 24 | 18 | 16

## Story Map
Epics |  | Service General - User Story Map
Epic 1 - User Account |  | Epic 1 - User Account | Epic 2 - Customize Search | Epic 3 - Job Advertisement | Epic 4 - Job Service Request | Epic 5 - Payment | Epic 6 - Control Management | Epic 7 - Feedback System
Epic 2 - Customize Search | User Stories | 1.3 Delete an Account |  |  | 4.2 Submit Job Service Request |  |  |  | Iteration 1
Epic 3 - Job Advertisement |  |  |  |  | 4.3 Accept Job Service Request
Epic 4 - Job Service Request |  |  |  |  | 4.4 Display Service Request Dashboard
Epic 5 - Payment |  |  |  |  | 4.5 Decline Job Service Request
Epic 6 - Control Management |  | 1.4 Update Profile | [5 empty] | 7.2 Edit feedback | Iteration 2
Epic 7 - Feedback System |  | 1.4 Account Logout | [5 empty] | 7.3 Delete feedback
7.4 Rate Service
|  |  | 2.1 Search by Location | 3.2 Close Advertisement Service Request |  |  |  |  | Iteration 3
2.3 Search by Service
|  |  | 2.2 Keyword Search |  |  |  |  | 5.3 Delete Payment Information | Iteration 4
5.1 Add Payment Information
5.2 Update Payment Information