## R1 I1
Task # | Iteration | Module Name | RCT.ID | Core Feature | Task Description | Start Date | End Date | Status | Task Owner
1 | R1 - I1 | User Account | 1.3 | Delete an account | Create Draft GUI Design and Layout | 2021-10-01 | 2021-10-04 | 100% | Sriram
2 | R1 - I1 | User Account | 1.3 | Delete an account | Develop and Implement GUI Layout | 2021-10-02 | 2021-10-04 | 100% | Melba
3 | R1 - I1 | User Account | 1.3 | Delete an account | Implement validation on fields to ensure accurate modifications: Email Address is required and not null/blank | 2021-10-03 | 2021-10-04 | 100% | Melba
4 | R1 - I1 | User Account | 1.3 | Delete an account | Implement validation on fields to ensure accurate modifications: Password needs to meet validatoin criteria | 2021-10-03 | 2021-10-04 | 100% | Melba
5 | R1 - I1 | User Account | 1.3 | Delete an account | Clarify Crosscuts and Test Cases | 2021-10-03 | 2021-10-04 | 100% | Rujul
6 | R1 - I1 | User Account | 1.3 | Delete an account | Crosscut: FV - Field Validation | 2021-10-03 | 2021-10-04 | 100% | Rujul
7 | R1 - I1 | User Account | 1.3 | Delete an account | DF-In - Data Flow | 2021-10-03 | 2021-10-04 | 100% | Rujul
8 | R1 - I1 | User Account | 1.3 | Delete an account | AU – Auditing | 2021-10-03 | 2021-10-04 | 100% | Rujul
9 | R1 - I1 | User Account | 1.3 | Delete an account | Create test cases for functionality | 2021-10-04 | 2021-10-06 | 100% | Tanvi
10 | R1 - I1 | User Account | 1.3 | Delete an account | Create test cases for validation | 2021-10-04 | 2021-10-06 | 100% | Tanvi
11 | R1 - I1 | User Account | 1.3 | Delete an account | Execute test cases and document in test execution log | 2021-10-04 | 2021-10-06 | 100% | Tanvi
12 | R1 - I1 | Job Service Request | 4.2 | Submit Job Service Request | Create Draft GUI Design and Layout | 2021-10-06 | 2021-10-07 | 100% | Sriram
13 | R1 - I1 | Job Service Request | 4.2 | Submit Job Service Request | Develop and Implement GUI Layout | 2021-10-07 | 2021-10-09 | 100% | Melba
14 | R1 - I1 | Job Service Request | 4.2 | Submit Job Service Request | Implement validation on fields to ensure accurate modifications: First Name is required and not null/blank | 2021-10-07 | 2021-10-09 | 100% | Melba
15 | R1 - I1 | Job Service Request | 4.2 | Submit Job Service Request | Implement validation on fields to ensure accurate modifications: Last Name is required and not null/blank | 2021-10-07 | 2021-10-09 | 100% | Melba
16 | R1 - I1 | Job Service Request | 4.2 | Submit Job Service Request | Clarify Crosscuts and Test Cases | 2021-10-10 | 2021-10-11 | 100% | Rujul
17 | R1 - I1 | Job Service Request | 4.2 | Submit Job Service Request | Crosscut: FV - Field Validation | 2021-10-10 | 2021-10-11 | 100% | Rujul
18 | R1 - I1 | Job Service Request | 4.2 | Submit Job Service Request | Crosscut: DF-In - Data Flow | 2021-10-10 | 2021-10-11 | 100% | Rujul
19 | R1 - I1 | Job Service Request | 4.2 | Submit Job Service Request | Crosscut: DF-Out - Data Flow Out | 2021-10-10 | 2021-10-11 | 100% | Rujul
20 | R1 - I1 | Job Service Request | 4.2 | Submit Job Service Request | Create test cases for functionality | 2021-10-10 | 2021-10-11 | 100% | Tanvi
21 | R1 - I1 | Job Service Request | 4.2 | Submit Job Service Request | Create test cases for validation | 2021-10-10 | 2021-10-11 | 100% | Tanvi
22 | R1 - I1 | Job Service Request | 4.2 | Submit Job Service Request | Execute test cases and document in test execution log | 2021-10-10 | 2021-10-11 | 100% | Tanvi
23 | R1 - I1 | Job Service Request | 4.3 | Accept Job Service Request | Create Draft GUI Design and Layout | 2021-10-11 | 2021-10-12 | 100% | Sriram
24 | R1 - I1 | Job Service Request | 4.3 | Accept Job Service Request | Develop and Implement GUI Layout | 2021-10-12 | 2021-10-13 | 100% | Melba
25 | R1 - I1 | Job Service Request | 4.3 | Accept Job Service Request | Create Accept Button | 2021-10-12 | 2021-10-13 | 100% | Melba
26 | R1 - I1 | Job Service Request | 4.3 | Accept Job Service Request | Crosscut ET – Entitlements | 2021-10-13 | 2021-10-14 | 100% | Rujul
27 | R1- l1 | Job Service Request | 4.3 | Accept Job Service Request | Crosscut DDV - Data Dependency Validation | 2021-10-13 | 2021-10-14 | 100% | Rujul
28 | R1- l1 | Job Service Request | 4.3 | Accept Job Service Request | Create test cases for functionality | 2021-10-14 | 2021-10-15 | 100% | Tanvi
29 | R1 - I1 | Job Service Request | 4.3 | Accept Job Service Request | Create test cases for validation | 2021-10-14 | 2021-10-15 | 100% | Tanvi
30 | R1 - I1 | Job Service Request | 4.3 | Accept Job Service Request | Execute test cases and document in test execution log | 2021-10-14 | 2021-10-15 | 100% | Tanvi
31 | R1 - I1 | Job Service Request | 4.5 | Decline Job Service Request | Create Draft GUI Design and Layout | 2021-10-15 | 2021-10-16 | 100% | Sriram
32 | R1 - I1 | Job Service Request | 4.5 | Decline Job Service Request | Develop and Implement GUI Layout | 2021-10-15 | 2021-10-16 | 100% | Melba
33 | R1 - I1 | Job Service Request | 4.5 | Decline Job Service Request | Create Decline Button | 2021-10-15 | 2021-10-16 | 100% | Melba
34 | R1 - I1 | Job Service Request | 4.5 | Decline Job Service Request | Crosscut: DF-In - Data Flow In | 2021-10-16 | 2021-10-17 | 100% | Rujul
35 | R1 - I1 | Job Service Request | 4.5 | Decline Job Service Request | Crosscut: DF-Out - Data Flow Out | 2021-10-16 | 2021-10-17 | 100% | Rujul
36 | R1 - I1 | Job Service Request | 4.5 | Decline Job Service Request | Create test cases for functionality | 2021-10-17 | 2021-10-18 | 100% | Tanvi
37 | R1 - I1 | Job Service Request | 4.5 | Decline Job Service Request | Create test cases for validation | 2021-10-17 | 2021-10-18 | 100% | Tanvi
38 | R1 - I1 | Job Service Request | 4.5 | Decline Job Service Request | Execute test cases and document in test execution log | 2021-10-17 | 2021-10-18 | 100% | Tanvi
39 | R1 - I1 | Job Service Request | 4.4 | Display Service Request Dashboard | Create Draft GUI Design and Layout | 2021-10-17 | 2021-10-18 | 100% | Melba
40 | R1 - I1 | Job Service Request | 4.4 | Display Service Request Dashboard | Develop and Implement GUI Layout | 2021-10-17 | 2021-10-18 | 100% | Melba
41 | R1 - I1 | Job Service Request | 4.4 | Display Service Request Dashboard | CN - Connectivity | 2021-10-17 | 2021-10-18 | 100% | Tanvi
42 | R1 - I1 | Job Service Request | 4.4 | Display Service Request Dashboard | Crosscut: DF-Out - Data Flow Out | 2021-10-17 | 2021-10-18 | 100% | Tanvi
43 | R1 - I1 | Job Service Request | 4.4 | Display Service Request Dashboard | DDV - Data Dependency Validation | 2021-10-17 | 2021-10-18 | 100% | Tanvi
44 | R1 - I1 | Job Service Request | 4.4 | Display Service Request Dashboard | Create test cases for functionality | 2021-10-17 | 2021-10-18 | 100% | Tanvi
45 | R1 - I1 | Job Service Request | 4.4 | Display Service Request Dashboard | Create test cases for validation | 2021-10-17 | 2021-10-18 | 100% | Tanvi
46 | R1 - I1 | Job Service Request |  | Display Service Request Dashboard | Execute test cases and document in test execution log | 2021-10-17 | 2021-10-18 | 100% | Tanvi
47 | R1 - I2 | User Account | 1.4 | Update Profile | Create Draft GUI Design and Layout | 2021-10-18 | 2021-10-19 | 100% | Melba
48 | R1 - I2 | User Account | 1.4 | Update Profile | Development and Implement GUI Layout | 2021-10-18 | 2021-10-19 | 100% | Melba
49 | R1 - I2 | User Account | 1.4 | Update Profile | DF-In - Data Flow In | 2021-10-18 | 2021-10-19 | 100% | Tanvi
50 | R1 - I2 | User Account | 1.4 | Update Profile | DF-Out - Data Flow Out | 2021-10-18 | 2021-10-19 | 100% | Tanvi
51 | R1 - I2 | User Account | 1.4 | Update Profile | FV - Field Validation | 2021-10-18 | 2021-10-19 | 100% | Tanvi
52 | R1 - I2 | User Account | 1.4 | Update Profile | Create test cases for functionality | 2021-10-29 | 2021-11-01 | 100% | Rujul
53 | R1 - I2 | User Account | 1.4 | Update Profile | Create test cases for validation | 2021-10-29 | 2021-11-01 | 100% | Rujul
54 | R1 - I2 | User Account | 1.4 | Update Profile | Execute test cases and document in test execution log | 2021-10-29 | 2021-11-01 | 100% | Rujul
55 | R1 - I2 | User Account | 1.5 | Account Logout | Create Draft GUI Design and Layout | 2021-10-19 | 2021-10-20 | 100% | Melba
56 | R1 - I2 | User Account | 1.5 | Account Logout | Development and Implement GUI Layout | 2021-10-19 | 2021-10-20 | 100% | Melba
57 | R1 - I2 | User Account | 1.5 | Account Logout | AU - Auditing | 2021-10-19 | 2021-10-20 | 100% | Tanvi
58 | R1 - I2 | User Account | 1.5 | Account Logout | Create test cases for functionality | 2021-10-29 | 2021-11-01 | 100% | Rujul
59 | R1 - I2 | User Account | 1.5 | Account Logout | Create test cases for validation | 2021-10-29 | 2021-11-01 | 100% | Rujul
60 | R1 - I2 | User Account | 1.5 | Account Logout | Execute test cases and document in test execution log | 2021-10-29 | 2021-11-01 | 100% | Rujul
61 | R1 - I2 | Feedback System | 7.2 | Edit Feedback | Create Draft GUI Design and Layout | 2021-10-20 | 2021-10-21 | 100% | Melba
62 | R1 - I2 | Feedback System | 7.2 | Edit Feedback | Development and Implement GUI Layout | 2021-10-20 | 2021-10-21 | 100% | Melba
63 | R1 - I2 | Feedback System | 7.2 | Edit Feedback | DF-In - Data Flow In | 2021-10-20 | 2021-10-21 | 100% | Tanvi
64 | R1 - I2 | Feedback System | 7.2 | Edit Feedback | DF-Out - Data Flow Out | 2021-10-20 | 2021-10-21 | 100% | Tanvi
65 | R1 - I2 | Feedback System | 7.2 | Edit Feedback | FV - Field Validation | 2021-10-20 | 2021-10-21 | 100% | Tanvi
66 | R1 - I2 | Feedback System | 7.2 | Edit Feedback | AU - Auditing | 2021-10-20 | 2021-10-21 | 100% | Tanvi
67 | R1 - I2 | Feedback System | 7.2 | Edit Feedback | Create test cases for functionality | 2021-10-29 | 2021-11-01 | 100% | Rujul
68 | R1 - I2 | Feedback System | 7.2 | Edit Feedback | Create test cases for validation | 2021-10-29 | 2021-11-01 | 100% | Rujul
69 | R1 - I2 | Feedback System | 7.2 | Edit Feedback | Execute test cases and document in test execution log | 2021-10-29 | 2021-11-01 | 100% | Rujul
70 | R1 - I2 | Feedback System | 7.3 | Delete Feedback | Create Draft GUI Design and Layout | 2021-10-21 | 2021-10-22 | 100% | Melba
71 | R1 - I2 | Feedback System | 7.3 | Delete Feedback | Development and Implement GUI Layout | 2021-10-21 | 2021-10-22 | 100% | Melba
72 | R1 - I2 | Feedback System | 7.3 | Delete Feedback | DF-In - Data Flow In | 2021-10-21 | 2021-10-22 | 100% | Tanvi
73 | R1 - I2 | Feedback System | 7.3 | Delete Feedback | AU - Auditing | 2021-10-21 | 2021-10-22 | 100% | Tanvi
74 | R1 - I2 | Feedback System | 7.3 | Delete Feedback | Create test cases for functionality | 2021-10-29 | 2021-11-01 | 100% | Rujul
75 | R1 - I2 | Feedback System | 7.3 | Delete Feedback | Create test cases for validation | 2021-10-29 | 2021-11-01 | 100% | Rujul
76 | R1 - I2 | Feedback System | 7.3 | Delete Feedback | Execute test cases and document in test execution log | 2021-10-29 | 2021-11-01 | 100% | Rujul
77 | R1 - I2 | Feedback System | 7.4 | Rate Service | Create Draft GUI Design and Layout | 2021-10-23 | 2021-10-24 | 100% | Melba
78 | R1 - I2 | Feedback System | 7.4 | Rate Service | Development and Implement GUI Layout | 2021-10-23 | 2021-10-24 | 100% | Melba
79 | R1 - I2 | Feedback System | 7.4 | Rate Service | DF-In - Data Flow In | 2021-10-23 | 2021-10-24 | 100% | Tanvi
80 | R1 - I2 | Feedback System | 7.4 | Rate Service | DF-Out - Data Flow Out | 2021-10-23 | 2021-10-24 | 100% | Tanvi
81 | R1 - I2 | Feedback System | 7.4 | Rate Service | Create test cases for functionality | 2021-10-29 | 2021-11-01 | 100% | Rujul
82 | R1 - I2 | Feedback System | 7.4 | Rate Service | Create test cases for validation | 2021-10-29 | 2021-11-01 | 100% | Rujul
83 | R1 - I2 | Feedback System | 7.4 | Rate Service | Execute test cases and document in test execution log | 2021-10-29 | 2021-11-01 | 100% | Rujul