## Sheet1
Color Coding |  |  | Completed |  |  |  | SPRING 2021
In Progress
[6 empty] | Week # | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
[6 empty] | Date | 2021-01-26 | 2021-02-02 | 2021-02-09 | 2021-02-16 | 2021-02-23 | 2021-03-02 | 2021-03-09 | 2021-03-23 | 2021-04-06 | 2021-04-13 | 2021-04-20 | 2021-04-27 | 2021-05-04 | 2021-05-11
Project Phase | Activity |  | Owners | Start Date | End Date | Progress %
Project Initiation | Project proposal discussion |  | All | 2021-01-26 | 2021-02-01 | 100%
| Prioritize project ideas |  | All | 2021-01-26 | 2021-02-09 | 100%
| Estimation of cost and schedule |  | Harrison Yang | 2021-01-26 | 2021-02-16 | 100%
| Development of the business case |  | Darshan Venkata | 2021-01-26 | 2021-02-02 | 100%
| PID |  | Harrison Yang | 2021-02-02 | 2021-02-16 | 100%
| Business Case |  | All | 2021-01-26 | 2021-02-09 | 100%
| Project environment preparation |  | Harrison Yang | 2021-01-26 | 2021-02-03 | 100%
MILESTONE 1: INITIAL PROJECT PLAN
Requirement Analysis | Production of project schedule |  | Harrison, Darshan | 2021-02-09 | 2021-02-23 | 100%
| Requirements Types, include the tasks in Project Plan |  | Harrison | 2021-02-09 | 2021-02-23 | 100%
| Organize Project Team |  | Harrison Yang | 2021-02-02 | 2021-02-16 | 100%
| Define Business Requirements |  | Harrison, Darshan, Shaina | 2021-02-23 | 2021-03-02 | 100%
| BRM Diagram, define User Roles |  | Darshan, Melba | 2021-02-16 | 2021-02-23 | 100%
| RCT (includes supplementary requirements) |  | Harrison, Darshan | 2021-02-23 | 2021-03-02 | 100%
| Functional Decomposition (assign SME), Fishbone Diagram |  | Artsiom, Melba, Shaina | 2021-02-23 | 2021-03-02 | 100%
| Business Use Cases, UML Analysis Diagram |  | Shaina, Darshan | 2021-02-23 | 2021-03-02 | 100%
| Context Diagram, System Interface Table |  | Artsiom | 2021-02-16 | 2021-02-23 | 100%
| Functional Requirements (User Stories) |  | Artsiom, Melba | 2021-03-02 | 2021-03-09 | 100%
| Data-flow Diagrams (logical, physical) |  | Artsiom, Melba | 2021-03-02 | 2021-03-09 | 100%
| Complete Home Page Demo |  | Artsiom, Melba | 2021-03-02 | 2021-03-09 | 100%
MILESTONE 2: REQUIREMENTS COMPLETED
Design | Architecture design |  | Melba Moro | 2021-04-06 | 2021-04-13 | 100%
| Home Page Design |  | Artsiom, Melba | 2021-03-02 | 2021-03-09 | 100%
| Database Design |  | Artsiom Naslednikau | 2021-03-23 | 2021-04-06 | 100%
| System Interface Design |  | Melba Moro | 2021-04-06 | 2021-04-13 | 100%
| User interface design |  | Artsiom Naslednikau | 2021-04-06 | 2021-04-13 | 100%
MILESTONE 3: DESIGN COMPLETED
Code | 1.1 Create an Account | GUI & Functionality Design | Melba, Artsiom | 2021-03-23 | 2021-04-13 | 100%
|  | Back-End | Melba, Artsiom | 2021-03-23 | 2021-04-13 | 100%
| Performance Logging | Crosscut | Melba, Artsiom | 2021-03-23 | 2021-04-13 | 100%
| 1.2 Sign into Account | GUI & Functionality Design | Melba, Artsiom | 2021-03-23 | 2021-04-13 | 100%
|  | Back-End | Melba, Artsiom | 2021-03-23 | 2021-04-13 | 100%
| DF-In - Data Flow In | Crosscut | Melba, Artsiom | 2021-03-23 | 2021-04-13 | 100%
| 4.1 Register Job Service | GUI & Functionality Design | Melba, Artsiom | 2021-03-30 | 2021-04-13 | 100%
|  | Back-End | Melba, Artsiom | 2021-03-30 | 2021-04-13 | 100%
| FV - Field Validation | Crosscut | Melba, Artsiom | 2021-03-23 | 2021-04-13 | 75%
| 7.1 Create Review | GUI & Functionality Design | Melba, Artsiom | 2021-03-30 | 2021-04-13 | 100%
|  | Back-End | Melba, Artsiom | 2021-03-30 | 2021-04-13 | 100%
| Auditing | Crosscut | Melba, Artsiom | 2021-03-30 | 2021-04-13 | 100%
MILESTONE 4: CODING COMPLETED
Integration & Testing | Overall Testing Strategy |  | Tanvi, Shaina | 2021-04-06 | TBD | 100%
| Evaluate Features to be Tested |  | Tanvi, Shaina | 2021-04-06 | TBD | 100%
| 1.1 Create an Accout | Design Test Cases | Tanvi, Shaina | 2021-04-06 | TBD | 100%
|  | Execute Test Cases | Tanvi, Shaina | 2021-04-06 | TBD | 100%
|  | Anaylze Test Results | Tanvi, Shaina | 2021-04-06 | TBD | 100%
| 1.2 Sign into Account | Design Test Cases | Tanvi, Shaina | 2021-04-06 | TBD | 100%
|  | Execute Test Cases | Tanvi, Shaina | 2021-04-06 | TBD | 100%
|  | Anaylze Test Results | Tanvi, Shaina | 2021-04-06 | TBD | 100%
| 4.1 Register Job Service | Design Test Cases | Tanvi, Shaina | 2021-04-06 | TBD | 50%
|  | Execute Test Cases | Tanvi, Shaina | 2021-04-06 | TBD | 50%
|  | Anaylze Test Results | Tanvi, Shaina | 2021-04-06 | TBD | 50%
| 7.1 Create Review | Design Test Cases | Tanvi, Shaina | 2021-04-06 | TBD | 50%
|  | Execute Test Cases | Tanvi, Shaina | 2021-04-06 | TBD | 50%
|  | Anaylze Test Results | Tanvi, Shaina | 2021-04-06 | TBD | 50%
Implementation | Deploy Application For Presentation Demo |  | TBD | 2021-04-06 | 2021-04-13 | 0%
MILESTONE 5: TESTING COMPLETED
Presentation | Prepare Presentation of Demo |  | All | 2021-04-20 | 2021-04-27 | 0%